## Project Steps
Project Steps/Assignments | Task Survey |  |  |  |  | Task Assignments |  |  |  | Status
Steps | I'd like to work on this | No thanks I'd rather die | This is a strength of mine | Not my forte | Neutral | Week 1 |  |  |  | Week 2 |  | Week 3
1. Collect Data (datasources) | Andrej | Cat |  | Stephanie |  | Done 2/14 |  |  |  | Status 2/16 | Status 2/18 | Status 2/21/2021 | Status 2/23/2021 | To do for 2/26 | To do for 2/29
[10 empty] | Done | Done 2/18 | Update Readme w/current Datasets | Patrick found 2 more datasets | Decide how many datasets we want to cap at | patrick looking at monthly datasets
Josh
McKenzie
2. Create/Upload into Database | Patrick |  | Cat - If SQL yes if Mongo no | McKenzie |  | Mongo - Patrick (Josh to connect w/Patrick) |  |  |  | Database | Database Update | Database Update | Database Update | Database Update
| Josh | [8 empty] | Patrick - creating database in Mongo once he has 4 clean files | Mongo Database created 2/18 | Connect to Josh/Patrick Mongo | Done | Add new datasets | everyone upload datasets into Mongo | Done
[10 empty] | Patrick - creating ERD | Rought Draft ERD created 2/18 | Update 12 databases into Mongo (see below) | Done
3. ETL data (process data/panda-fy etc) | Andrej |  |  |  | Cat | ETL Data Set 1 | ETL Data Set 2 | ETL Data Set 3 | ETL Data Set 4 | ETL Data Update | ETL Data Update | ETL Data Update | ETL Data Update | ETL Data Update
| Stephanie |  |  |  |  | Stephanie | Andre | Patrick | Josh done | Each person will upload datasets and clean data (data_clean) | Clean Datasets uploaded into Mongo | Upload Raw Data - (4 total) | Done | ETL clean up unemployment rate - Cat | cat ETL | Done
| Patrick |  |  |  |  | Population Change | Total employment | GDP | Unemployment rate |  |  | Upload Clean Data - (4 total) | Done | ETL clean up Labor Force - Josh | McKenzie ETL | Done
| Josh | [10 empty] | Upload Predicted Data (rate of change/rank) - (4 total) | Done |  | andrej divide up monthly | Done
4. Look at features for machine learning (research and testing models) | Andrej |  |  | Cat |  | ML Data Set 1 | ML Data Set 2 | ML Data Set 3 | ML Data Set 4 | ML Data Update | ML Data Update | ML Data Update | ML Data Update | ML Data Update
| Stephanie |  |  |  |  | Stephanie | Andre | Patrick | Josh | Cat - Compare accucracy on 2019 data to see accucracy of model - LR | Done 2/18 (Tested accucracy of model on rate of change numbers and original numbers | Re run all data w/original numbers instead of rank (each dataset |  | Decide on MLM model w/James - Entire team | Josh to update model w/new datasets with ARIMA
[6 empty] | Population Change | Total Employment | GDP | Unemployment Rate | Andre - Test various models ( | Done 2/18 - Tested Random Forest | Then will merge all datasets into 1 dataset and run RFC/NN | Mockup (Josh ranked) |  | Cat write up of MLM
[10 empty] | Stephanie - Look into confidence /Bolinger Bands | Done (will revisit when further down the road
5. Develop API/Front end (maps, visualizetion, web app etc) | McKenzie |  | Cat - Tableau yes if Java no | Andrej | Cat | Visualization Update |  |  |  | Visualization Update | Visualization Update | Visualization Update | Visualization Update | Visualization Update
| Cat |  |  |  |  | Patrick -Heroku |  |  |  | McKenzie - Blueprint of Dashboard | Rought draft of heat map using 0's, 1's | Patrick/McKenzie - gameplan for Sunday | Create Vizio mock up doc | Rough Draft/Mock of Visualization - Stephanie/Cat
| Patrick |  |  |  |  | McKenzie, Cat | [5 empty] | heroku (hosting site) - research | Heroku up | Andrej/Stephanie - Continue working on charts | 6 graphs - Andrej (6 scatter plots) - use annual for graphs?
[6 empty] | All of Us at Some Point TBD (Discuss Tonight) | [5 empty] | McKenzie looking into visualizing |  | Assign tasks for Visualization
6. Google Slides (presentation) | McKenzie |  | Stephanie |  |  | Presentation Update |  |  |  | Presentation Update | Presentation Update | Presentation Update | Presentation Update | Presentation Update
| Cat |  |  |  |  | McKenzie,Stephanie, Cat create slides |  |  |  | Cat Create Rough Draft on Google Slides | Template created - link shared in readme and discord | Cat to continue working on | Talk how to frame pitch | Continue updating slides and how to frame pitch
Everyone Present
Get more details from James
Also comment below with any preference of database used, programming language, or visualization you want to use in project
Database | Programming Langauge |  | Visualization

## Visiualization Tasks
Visualization Breakdown of Tasks
Home | Table/Map | Charts | About | Bootstrap | Finishing touches
Description - | McKenzie | Population - Stephanie | Write up - | Research - | Patrick
Ranking Result Charts - | ? | Employment - Andrej |  | Implement -
Statistics - |  | GDP -
? |  | Unemployment Rate -
Labor Force -
Unemployment -
Ranking ?

## Remaining Steps
Remaining Tasks | Review and see what we need to add
Datasets | Mongo | ETL | MLM | Visualization | Presentation
Patrick finding remaining datasets | Whoever ETL'ed upload to Mongo | Unemployment Rate - Cat | Update - Josh | See Separate Tab | Continue working on presentation - Cat and whoever else
|  | Labor Force - Josh | Tweak - ?
|  | ? | Cat - Write up MLM Document
?