## Project Steps
Project Steps/Assignments | Task Survey |  |  |  |  | Task Assignments |  |  |  | Status
Steps | I'd like to work on this | No thanks I'd rather die | This is a strength of mine | Not my forte | Neutral | Week 1 |  |  |  | Week 2 |  | Week 3 |  |  | Week 4 |  |  | Week 5 Presentation
1. Collect Data (datasources) | Andrej | Cat |  | Stephanie |  | Done 2/14 |  |  |  | Status 2/16 | Status 2/18 | Status 2/21/2021 | Status 2/23/2021 | Status 2/25/2021 | Status 2/28/2021 | Status 3/2/2021 | Status 3/4/2021 | To do 3/7/2021 | To do 3/9/2021 | To do 3/11/2021
[10 empty] | Done | Done 2/18 | Update Readme w/current Datasets | Patrick found 2 more datasets | Decide how many datasets we want to cap at | 6 total datasets | patrick looking at monthly datasets | 8 total datasets | All datasets monthly/final | None | None
Josh
McKenzie
2. Create/Upload into Database | Patrick |  | Cat - If SQL yes if Mongo no | McKenzie |  | Mongo - Patrick (Josh to connect w/Patrick) |  |  |  | Database | Database Update | Database Update | Database Update | Database Update | Database Update | Database Update | Database Update | Database Update | Database Update | Database Update
| Josh | [8 empty] | Patrick - creating database in Mongo once he has 4 clean files | Mongo Database created 2/18 | Connect to Josh/Patrick Mongo | Done | Add new datasets | Added Datasets - found monthly | everyone upload datasets into Mongo | 8 datasets uploaded | Added new datasets | All datasets ploaded | None
[10 empty] | Patrick - creating ERD | Rought Draft ERD created 2/18 | Update 12 databases into Mongo (see below) | Done
3. ETL data (process data/panda-fy etc) | Andrej |  |  |  | Cat | ETL Data Set 1 | ETL Data Set 2 | ETL Data Set 3 | ETL Data Set 4 | ETL Data Update | ETL Data Update | ETL Data Update | ETL Data Update | ETL Data Update | ETL Data Update | ETL Data Update | ETL Data Update | ETL Data Update | ETL Data Update | ETL Data Update
| Stephanie |  |  |  |  | Stephanie | Andre | Patrick | Josh done | Each person will upload datasets and clean data (data_clean) | Clean Datasets uploaded into Mongo | Upload Raw Data - (4 total) | Done | ETL clean up unemployment rate - Cat |  | cat ETL - Done | 8 datasets cleaned | Done | Done | None
| Patrick |  |  |  |  | Population Change | Total employment | GDP | Unemployment rate |  |  | Upload Clean Data - (4 total) | Done | ETL clean up Labor Force - Josh |  | McKenzie ETL - Done |  | Done
| Josh | [10 empty] | Upload Predicted Data (rate of change/rank) - (4 total) | Done |  |  | andrej divide up monthly - Done |  | Done
4. Look at features for machine learning (research and testing models) | Andrej |  |  | Cat |  | ML Data Set 1 | ML Data Set 2 | ML Data Set 3 | ML Data Set 4 | ML Data Update | ML Data Update | ML Data Update | ML Data Update | ML Data Update | ML Data Update | ML Data Update | ML Data Update | ML Data Update | ML Data Update | ML Data Update
| Stephanie |  |  |  |  | Stephanie | Andre | Patrick | Josh | Cat - Compare accucracy on 2019 data to see accucracy of model - LR | Done 2/18 (Tested accucracy of model on rate of change numbers and original numbers | Re run all data w/original numbers instead of rank (each dataset |  | Decide on MLM model w/James - Entire team | Josh to figure out Arima | Josh to update model w/new datasets with ARIMA - Done | Everyone run 1 ARIMA model on final dataset | Work on ARIMA writeup - Josh |  | None
[6 empty] | Population Change | Total Employment | GDP | Unemployment Rate | Andre - Test various models ( | Done 2/18 - Tested Random Forest | Then will merge all datasets into 1 dataset and run RFC/NN | Mockup (Josh ranked) |  |  | Cat write up of MLM - Done |  | Work on ARIMA flowchart - Stephanie
[10 empty] | Stephanie - Look into confidence /Bolinger Bands | Done (will revisit when further down the road
5. Develop API/Front end (maps, visualizetion, web app etc) | McKenzie |  | Cat - Tableau yes if Java no | Andrej | Cat | Visualization Update |  |  |  | Visualization Update | Visualization Update | Visualization Update | Visualization Update | Visualization Update | Visualization Update | Visualization Update | Visualization Update | Visualization Update | Visualization Update | Visualization Update
| Cat |  |  |  |  | Patrick -Heroku |  |  |  | McKenzie - Blueprint of Dashboard | Rought draft of heat map using 0's, 1's | Patrick/McKenzie - gameplan for Sunday | Create Vizio mock up doc | Rough Draft/Mock of Visualization - Stephanie/Cat | Patrick worked on site | Patrick continued style updates | Patrick continue style updates | Patrick continue style updates | Style updates | none
| Patrick |  |  |  |  | McKenzie, Cat | [5 empty] | heroku (hosting site) - research | Heroku up | Andrej/Stephanie - Continue working on charts |  | Andrej worked on charts | Andrej finished charts | Work on first page charts - Andrej
[6 empty] | All of Us at Some Point TBD (Discuss Tonight) | [5 empty] | McKenzie looking into visualizing |  | Assign tasks for Visualization
6. Google Slides (presentation) | McKenzie |  | Stephanie |  |  | Presentation Update |  |  |  | Presentation Update | Presentation Update | Presentation Update | Presentation Update | Presentation Update | Presentation Update | Presentation Update | Presentation Update | Presentation Update | Presentation Update | Presentation Update
| Cat |  |  |  |  | McKenzie,Stephanie, Cat create slides |  |  |  | Cat Create Rough Draft on Google Slides | Template created - link shared in readme and discord | Cat to continue working on | Talk how to frame pitch | Continue updating slides and how to frame pitch | Continue editing slides | Continue editing slides | Continue editing slides | Continue editing slides | finalize presentation for Tuesday | Present!
[6 empty] | Everyone Present | [11 empty] | Split up presentation
Get more details from James
Also comment below with any preference of database used, programming language, or visualization you want to use in project
Database | Programming Langauge |  | Visualization

## Visiualization Tasks
Visualization Breakdown of Tasks
Home | Table/Map | Charts | About | Bootstrap | Finishing touches
Description - | McKenzie | Population - Stephanie | Write up - | Research - | Patrick
Ranking Result Charts - |  | Employment - Andrej |  | Implement -
Statistics - |  | GDP -
Unemployment Rate -
Labor Force -
Unemployment -
Ranking ?

## Remaining Steps
Remaining Tasks | Review and see what we need to add
Datasets | Mongo | ETL | MLM | Visualization | Presentation
Patrick finding remaining datasets | Whoever ETL'ed upload to Mongo | Unemployment Rate - Cat | Update - Josh | See Separate Tab | Continue working on presentation - Cat and whoever else
|  | Labor Force - Josh | Tweak - ?
|  | ? | Cat - Write up MLM Document
?